ENGINEERING DELIVERY PLAN

# Phased Build Plan

Implementation sequence from empty repository to adaptive chess trainer

Project: Chess App (working title)

Version: 1.0

Date: June 13, 2026

Status: Planning baseline

Planning assumption: The repository is currently empty. Estimates are directional engineering effort for one experienced full-time engineer and exclude App Store review, legal review, branding, and external model-training time.

# 1. Delivery Strategy

The build proceeds through vertical slices. Each phase must leave the product runnable, tested, and deployable. The backend begins as a modular FastAPI application with a separate worker and AI service contract. PostgreSQL owns durable state; Redis supports coordination, presence, queues, and locks. The iOS app adopts server authority early so local-only assumptions do not leak into multiplayer.

Correctness before scale: prove chess state transitions and persistence first.

Contracts before clients: stabilize API and WebSocket message envelopes with tests.

Single process before distributed complexity: introduce Redis-backed coordination only where a phase needs it.

Baseline AI before ML: preserve the product schedule even when a custom model is not ready.

Phase gates are mandatory: deferred features do not enter a phase without replacing an existing commitment.

# 2. Target Repository Structure

chess-app/
  apps/
    ios/                       # SwiftUI application and Xcode project
  services/
    api/                       # FastAPI modular monolith
      app/
        api/                   # HTTP and WebSocket transport
        auth/                  # identity and authorization
        games/                 # domain model and commands
        matchmaking/           # invites and queues
        ai/                    # internal AI client/contract
        db/                    # sessions, models, migrations
        core/                  # settings, logging, telemetry
      tests/
    worker/                    # background analysis jobs
    ai/                        # inference service and baseline bots
  deploy/
    compose.yaml               # local and Coolify service definitions
    coolify/                   # environment and runbook notes
  docs/
  .github/workflows/

# 3. Technology Baseline

| Layer | Initial Choice | Reason |
| --- | --- | --- |
| iOS | Swift 6, SwiftUI, async/await | Native UX, App Store integration, clear state and concurrency model. |
| API | Python 3.13, FastAPI, Pydantic | Strong python-chess fit and native async WebSocket support. |
| Persistence | PostgreSQL, SQLAlchemy 2, Alembic | Transactional durable state and explicit migrations. |
| Coordination | Redis | Matchmaking queues, presence, locks, pub/sub, and transient state. |
| Rules | python-chess | Mature legal move, outcome, FEN, SAN, and PGN support. |
| Testing | pytest, async test client, Testcontainers where practical | Fast domain tests plus realistic integration coverage. |
| Delivery | Docker, Compose, Coolify, GitHub Actions | Reproducible local/staging/production deployment. |

Versions should be pinned during scaffolding after confirming current supported releases. The plan intentionally names technologies, not unverified version numbers.

# 4. Phase Overview

| Phase | Outcome | Indicative Effort |
| --- | --- | --- |
| 0. Foundation | Repository, CI, containers, configuration, observability baseline. | 3-5 days |
| 1. Chess Core | Authoritative game creation, legal moves, persistence, PGN. | 1-2 weeks |
| 2. Native Board | Playable SwiftUI board connected to backend game APIs. | 2-3 weeks |
| 3. AI Opponent | Server-backed baseline bots with difficulty and resilience. | 1-2 weeks |
| 4. Friend Multiplayer | Invite games, WebSockets, reconnects, presence. | 2-4 weeks |
| 5. Matchmaking | Queues, clocks, ratings, records, abuse limits. | 2-4 weeks |
| 6. Review | Game history, replay, analysis jobs, concise feedback. | 2-3 weeks |
| 7. ML Pipeline | Filtered datasets, evaluation harness, model registry. | 3-6 weeks |
| 8. Adaptive Coach | Personalized difficulty and weakness-oriented coaching. | 3-6+ weeks |

# 5. Phase 0 - Foundation and Scaffold

Objective: Turn the empty workspace into a reproducible development and deployment baseline.

## Deliverables

Git repository with documented branch and pull-request conventions.

FastAPI service package with typed settings, health/readiness endpoints, structured logging, and request IDs.

PostgreSQL and Redis containers with local Compose configuration and isolated test configuration.

SQLAlchemy session management and an initial Alembic migration.

pytest setup, linting, formatting, type checking, and a minimal GitHub Actions workflow.

Production Dockerfile, non-root runtime user, graceful shutdown, and Coolify environment template.

Architecture decision records for server authority, PostgreSQL durability, Redis responsibilities, and modular-monolith boundaries.

## Verification

One command starts API, PostgreSQL, and Redis locally.

Health check verifies process liveness; readiness verifies database and Redis connectivity.

Migration upgrade and downgrade run in CI against a clean database.

Static checks and tests pass without local-only dependencies.

Container image builds and starts with production settings.

Phase 0 exit gate: A clean checkout can be configured, tested, migrated, and started from documented commands. No gameplay behavior is required yet.

# 6. Phase 1 - Authoritative Chess Core

Objective: Complete a legal chess game through backend APIs with durable, reconstructable state.

## Deliverables

Game aggregate with participants, mode, status, result, FEN, sequence, and timestamps.

Create-game, get-game, submit-move, resign, and list-moves endpoints.

Move command contract with command ID and expected sequence.

python-chess adapter for UCI validation, SAN generation, outcomes, FEN, and PGN.

Transactional move append with unique idempotency constraint and per-game concurrency strategy.

Database models and migrations for users, games, and moves; development identity fixture.

Domain tests for standard moves and every special outcome.

## Verification

Automated API test plays a complete game to checkmate and validates final PGN.

Illegal, out-of-turn, stale, duplicate, and unauthorized commands are rejected deterministically.

Two simultaneous move submissions cannot both advance the same sequence.

Game state can be rebuilt from persisted moves and matches stored FEN.

No Redis dependency is required for correctness in this phase.

Phase 1 exit gate: A test client can create and finish valid games entirely through the API; persisted records reproduce every final position.

# 7. Phase 2 - Native iOS Board and Game Shell

Objective: Deliver a polished native board that consumes authoritative backend state.

## Deliverables

SwiftUI app shell with dependency injection, environment configuration, and feature-based organization.

Chess board rendering, orientation, piece assets, selection, move highlighting, and promotion UI.

Game state model that distinguishes local interaction state from authoritative server state.

Typed API client using async/await, cancellation, retry boundaries, and explicit errors.

Game screen controls for resign, restart/new game, loading, offline, and terminal outcomes.

Accessibility labels, dynamic layout checks, and primary state previews.

## Verification

The board renders correctly on supported phone sizes and both orientations if enabled.

Legal selections and promotions are usable with VoiceOver labels.

The app does not commit an unconfirmed move as canonical state.

Network failures preserve a recoverable UI and allow state refresh.

A user can complete a two-sided test game through the app against the Phase 1 API.

Phase 2 exit gate: The native client can reliably play and display a backend-owned game from start to completion.

# 8. Phase 3 - Single-Player AI

Objective: Make the product independently playable without waiting for a custom ML model.

## Deliverables

Internal AI request/response contract using FEN, difficulty, constraints, and correlation ID.

Baseline bot levels: random legal move, heuristic capture/check preference, and shallow search.

AI game orchestration that requests a move only after the human transition commits.

Validation of every AI-returned move before application.

Timeout, retry, fallback, and circuit-breaker behavior that cannot corrupt a game.

Model/bot version and think-time telemetry stored with each AI game.

## Verification

Each difficulty returns legal moves across a fixed position suite.

Invalid and timed-out AI responses produce controlled recovery or fallback.

Concurrent retries do not apply multiple AI moves.

A user can complete multiple AI games and see them in history.

Phase 3 exit gate: MVP 1 is release-candidate quality: users can play, resign, restart, and review games against at least two distinct baseline difficulty levels.

# 9. Phase 4 - Friend-Code Multiplayer

Objective: Support reliable private real-time games between two authenticated clients.

## Deliverables

Sign in with Apple or a documented temporary identity path for pre-release testing.

Private game creation, short expiring invite codes, join validation, and color assignment.

Authenticated WebSocket endpoint with connection lifecycle, heartbeat, and message envelopes.

Redis-backed presence and cross-instance pub/sub; PostgreSQL remains the durable game source.

Snapshot plus sequence-based recovery after reconnect or missed events.

Client WebSocket actor/service with backoff, cancellation, foreground/background handling, and resubscription.

## Verification

Two devices or simulators complete a private game with synchronized state.

Disconnecting either client for a defined interval does not lose committed moves.

A client missing events recovers from a canonical snapshot and current sequence.

An unauthorized user cannot observe or command a private game.

Multi-instance test proves events cross API process boundaries through Redis.

Phase 4 exit gate: MVP 2 is release-candidate quality: invite creation, joining, real-time play, and reconnect recovery work across multiple backend instances.

# 10. Phase 5 - Matchmaking, Clocks, and Ratings

Objective: Add fair quick play without weakening the correctness established in friend games.

## Deliverables

Redis matchmaking queues partitioned by time control and rating band.

Atomic pairing, cancellation, duplicate-entry prevention, and abandoned-match cleanup.

Server-owned clocks with latency policy, timeout adjudication, and persisted timing events.

Initial rating system with immutable rating events and provisional handling.

Win/loss/draw records, basic profile display, and rate limits.

Operational controls for queue depth, suspicious usage, and incident recovery.

## Verification

Load test pairs expected concurrent users without duplicate matches.

Clock outcomes remain correct through disconnects and process restarts.

Rating updates are transactional with game finalization and cannot apply twice.

Queue cancellation and timeout leave no stuck users or orphaned games.

Phase 5 exit gate: Quick play can be monitored and operated safely at the agreed launch concurrency, with deterministic game and rating outcomes.

# 11. Phase 6 - History, Review, and Coaching Baseline

Objective: Turn completed games into understandable learning moments.

## Deliverables

Paginated game history, replay controls, PGN export, and position navigation.

Background analysis jobs with explicit status, retry, and dead-letter behavior.

Engine-evaluation adapter isolated from the public game request path.

Detection of major swings, missed tactics, and key moments.

Short template-driven explanations with clear uncertainty and no fabricated claims.

Internal review tools for analysis quality and failed jobs.

## Verification

Analysis never blocks game completion or corrupts game records.

Jobs are idempotent and can be replayed after worker failure.

Feedback references the correct position and legal alternatives.

The app displays analysis progress, absence, and failure honestly.

Phase 6 exit gate: A completed game reliably produces a concise review that a beginner can connect to specific replay positions.

# 12. Phase 7 - Controlled ML Improvement Pipeline

Objective: Produce trustworthy training candidates without allowing raw gameplay to degrade the model.

## Deliverables

Immutable raw-game export with provenance, consent/retention controls, and schema version.

Filtering rules for corruption, low-signal positions, duplicates, and policy exclusions.

Reference-engine labeling jobs and reproducible feature generation.

Dataset versioning, train/validation/test split protection, and leakage checks.

Evaluation harness covering legality, tactical suites, baseline match play, latency, and resource use.

Model registry with candidate, approved, deployed, and retired states.

Manual promotion and rollback; no automatic production promotion.

## Verification

A dataset can be regenerated from source records and versioned configuration.

Evaluation produces repeatable results against fixed seeds and baselines.

A candidate that regresses legality, strength, latency, or stability cannot be promoted.

Production inference can be rolled back to a prior model without a client update.

Phase 7 exit gate: One candidate model completes the full offline pipeline and is promoted only after documented comparison with baseline bots.

# 13. Phase 8 - Adaptive AI Coach

Objective: Deliver the product's differentiator through personalized practice and feedback.

## Deliverables

Player weakness profile derived from reviewed games and bounded behavioral signals.

Adaptive opponent selection or move policy that targets weaknesses while maintaining a fair experience.

Difficulty calibration with measurable target win-rate or challenge bands.

Personalized post-game summaries and suggested practice themes.

Experiment framework with privacy-conscious assignment and guardrails.

User controls for personalization and data deletion.

## Verification

Personalization improves agreed learning or engagement measures without increasing illegal or unstable behavior.

Difficulty changes are explainable, bounded, and reversible.

Users with insufficient data receive a stable non-personalized experience.

Deleting an account removes or irreversibly anonymizes associated personalization data according to policy.

Phase 8 exit gate: The adaptive experience demonstrates a measurable benefit over static difficulty in a controlled test and meets privacy requirements.

# 14. Cross-Phase Quality Plan

| Test Layer | Required Coverage |
| --- | --- |
| Domain | Move legality, outcomes, clocks, ratings, command sequencing, idempotency, and state reconstruction. |
| API contract | Success and error envelopes, auth, pagination, versioning, stale-state recovery, and schema compatibility. |
| Integration | PostgreSQL transactions, migrations, Redis locks/pub-sub/queues, worker retries, and AI failures. |
| iOS | State reducers/models, API decoding, WebSocket recovery, board interactions, accessibility, and snapshot/UI smoke tests. |
| End to end | AI game, friend game, reconnect, timeout, result persistence, history, and analysis. |
| Operational | Container startup, health checks, backup restore, migration rollback, load, and deploy rollback. |

# 15. Coolify Deployment Plan

| Service | Phase Introduced | Deployment Responsibility |
| --- | --- | --- |
| chess-api | 0 | HTTP/WebSocket API, migrations as controlled release step, health/readiness. |
| postgres | 0 | Durable records, automated backups, restore test, persistent volume. |
| redis | 0; required by 4 | Coordination and queues; persistence policy based on recoverability needs. |
| chess-ai | 3 | Baseline/custom inference behind internal network and strict timeout. |
| chess-worker | 6 | Analysis and data jobs with independent scaling and failure handling. |
| admin-dashboard | Optional after 4 | Internal operations only; not a prerequisite for MVP. |

Separate staging and production environments, secrets, databases, domains, and deployment approvals.

Run migrations as an explicit, observable release action; avoid hidden startup migrations in multiple replicas.

Use rolling or blue/green deployment only after WebSocket draining and compatibility behavior are tested.

Backups are incomplete until a restore has been successfully exercised.

Keep the prior image and migration rollback instructions available for every production release.

# 16. First Scaffold Work Package

The immediate next implementation should cover Phase 0 plus the smallest Phase 1 vertical slice. This proves the architecture before the iOS project is generated.

Initialize repository, backend package, tooling, Dockerfile, Compose, CI, and environment examples.

Start PostgreSQL and Redis locally; add liveness/readiness checks.

Create initial users, games, and moves migrations.

Implement create game, retrieve game, and submit move using python-chess.

Add command ID and expected sequence to the move contract.

Test legal, illegal, stale, and duplicate moves plus one complete checkmate flow.

Document local commands and Coolify deployment inputs.

Scaffold definition of done: A clean environment can run the stack and execute an automated test that creates a game, submits legal moves, rejects an illegal move, and retrieves the resulting canonical state from PostgreSQL.

# 17. Decision Log for Scaffolding

| Decision | Baseline |
| --- | --- |
| Backend language | Python with FastAPI to keep python-chess in-process for the authoritative game core. |
| Architecture | Modular monolith API plus separate worker and AI deployment boundaries. |
| Durability | PostgreSQL is authoritative; Redis state must be reconstructable or explicitly disposable. |
| Client protocol | Command IDs, expected sequence, canonical responses, and snapshot recovery. |
| Identity in scaffold | Development identity seam with production auth interface; no hard-coded auth assumptions in domain logic. |
| API compatibility | Versioned `/v1` routes and explicit WebSocket message schema from the first public client. |

# 18. Deferred Until Triggered

Separate auth, matchmaking, and game microservices until scale or ownership requires independent deployment.

Kubernetes or bespoke orchestration while Coolify and Docker meet operational needs.

GraphQL, event sourcing, and a general message bus without a demonstrated requirement.

Chat, tournaments, clubs, subscriptions, and broad social features before core retention is established.

Automatic anti-cheat penalties or automated model deployment without human review.